## App - Bugs
Sr No | Bug ID | Bug Identified Date | Bug | Severity | Priority | Expected Result | Platform | Assign To | Developer Status | QA Status | Developer comment | QA Comment
1 | BUG 01 |  | after saying "hello" or other word which not mention in script then also script is going forward | High | Low | it should follow only script | iOS & Android |  | Not feasible | Not Feasible
2 | BUG 02 |  | after speaking only 1 line its scroll till 3 line | High | High | script speed should match with user | iOS |  | Resolved | QA Production Approved
3 | BUG 03 |  | in script colour option after change the colour we click on "ok" button its not woking | High | High | ok button should be working | iOS |  | Resolved | QA Production Approved | Resolved now
4 | BUG 04 |  | if we speak the script in reverse order its still scroll forward | High | High | if user follow the reverse order then script scroll should be stop | iOS & Android |  | Not feasible | Not Feasible
5 | BUG 05 |  | if we continue speaking according to the script but if we take little pause then slight script is scroll | High | Low | after pause script should be stop | iOS |  | Not feasible | Not Feasible | It may very on devices
6 | BUG 06 |  | in scripts section > on any script we select the two videos and click on delete button its delete the only one video | Medium | Medium | its should delete the all selected videos | iOS |  | Resolved | QA Production Approved
7 | BUG 07 |  | without "voice scroll" option we start video then pause button is not working | High | High | in normal video pause button should be working | iOS |  | Resolved | QA Production Approved | Resolved
8 | BUG 08 |  | after starting the video we are not able to change the quality | Low | Low | after starting the video quality option should be disappear | iOS & Android |  | Resolved | QA Production Approved |  | pending in android
9 | BUG 09 |  | in any script we go in draft section and start the video and after the completion of video its show in video section | High | High | its should be stored in draft section or we can disable the video option in draft section | iOS & Android |  | Not feasible | Not Feasible
10 | BUG 10 |  | after starting the video we on the "voice scroll" option then script forward is not woking | High | Low | after start the video "voice scroll" functionality should be working | iOS |  | Not feasible | Not Feasible
11 | BUG 11 |  | profile section> after click on my plan its take too much time to show our current plan | High | High | it should not take too much time to load | iOS |  | Resolved | QA Production Approved
12 | BUG 12 |  | profile section> after click on "restore backup" option page loading and its not stop(continuous loader) | Medium | Medium | restore backup functionality should be working | iOS |  | Resolved | QA Production Approved
13 | BUG 13 |  | profile section> after click on "create backup" option its not redirect to the other page | Medium | Medium | its should redirect to the other page | iOS & Android |  | Resolved | QA Production Approved
14 | BUG 14 |  | profile section> after click on "create backup" due to this option its generate the same scipt endless time and if we open any script then app is crashed(crash in ios only) | High | High | after using any functionality its should not create same script multiple time | iOS & Android |  | Resolved | QA Production Approved
15 | BUG 15 |  | voice scroll features is not visible | Low | Low | features should be visible | Android |  | Resolved | QA Production Approved
16 | BUG 16 |  | on recorded video we apply edit and rotate option app is crash | High | High | app should not crash while using this features | Android |  | Not feasible | Not Feasible | This issue is device specific, i tried some other android phone its working fine
17 | BUG 17 |  | in video we increase the speed but script run in normal speed | Medium | High | speed functionality should be working | iOS |  | Resolved | QA Production Approved |  | if we increase the script speed then its auto run without any voice
18 | BUG 18 |  | before start the video we change the script location and after the starting video slightly move to upper left | Medium | Medium | script should be stick according to user choice | iOS & Android |  | Resolved | QA Production Approved | Resolved
19 | BUG 19 |  | in generate ai script after selecting the topic and generate the script without selecting the language and its give the script in english | Low | Low | bydefault we have to select the english and if user want other language then they are able to change the language | iOS & Android |  | Not feasible | Not Feasible | Selecting a language is not mandatory. If no language is selected, the AI script is generated in English by default.
20 | BUG 20 |  | after selecting the language once again we click on language field and we are able to write | High | High | we should give the dropdown option so this issue not happen | Android |  | Resolved | QA Production Approved
21 | BUG 21 |  | in my plan we are on our current plan and continue button is working | High | High | if we are on current plan then continue button should be disable | iOS & Android |  | Not feasible | Not Feasible | its show all details from perticular store that is active
22 | BUG 22 |  | in my plan we have one current plan and select the other plan but we are not able to remove that selelct option | Low | Low | button should be woking properly | Android |  | Not feasible | Not Feasible
23 | BUG 23 |  | after subscribe any plan we are not able to view login and logout option | High | High | login and logout option should be there | Android |  | Not feasible | Not Feasible | On both iOS and Android platforms, when users purchase a plan via in-app purchases, we do not require or use a login system. All purchase data and backups are automatically linked to the user's main account — the Google account on Android and the iCloud account on iOS. Additionally, any backups created are also uploaded and associated with the user’s main account. Because of this direct linkage, there's no need for a separate login system. The login functionality is only used when redeeming a coupon code, such as from AppSumo. In all other cases, login and logout options are not required or shown within the app. | due to this user can delete the app and download again then their limit is start agian(it allow more 3 time free script)
24 | BUG 24 |  | in "import script" we are able to add mp3 file | Low | Low | its should not allow the mp3 file and show validation message | Android |  | Resolved | QA Production Approved
25 | BUG 25 |  | in instagram button add the easy speak page link instead of itechnotion | Low | Low | after the redirecting in instagram it should open easy speak page | iOS & Android |  | Not feasible | Not Feasible | Please note that the update is not from the mobile app. You'll need to update the link on the website — specifically, replace the current iTechnotion link in the Instagram button with the Easy Speak page link.
26 | BUG 26 |  | some times it show error like failed speech recognigation | High | Low | its should not show that kind of an error | iOS |  | Not feasible | Not Feasible
27 | BUG 27 |  | script is end but we are able to scroll up the script | High | High | after script user not able to scroll up | iOS & Android |  | Resolved | QA Production Approved
28 | BUG 28 |  | without voice scroll script is not auto moving | High | High | in without voice scroll script should be auto speed | iOS |  | Resolved | QA Production Approved
29 | BUG 29 |  | with voice scroll > we change the speed then script is auto scroll without any word | Low | Low | with voice scroll option its scroll with only voice | iOS |  | Resolved | QA Production Approved
30 | BUG 30 |  | after complete the video we edit the video and save as a draf video but its not save in draft video | High | High | its should save in draft | iOS |  | Resolved | QA Production Approved
31 | BUG 31 |  | after restore backup its render the other script is locked | High | High | its not render the other script is locked | iOS |  |  | QA Production Approved
32 | BUG 32 |  | if we logout then its not stored our past scripts | High | High | its should store the past script also | iOS |  |  | QA Production Approved
33 | BUG 33 |  | in select language we type hindi in english then its not fetch the hindi language | Medium | Medium | its should fetch the language | iOS |  | Resolved | QA Production Approved
34 | BUG 34 |  | in my current plan sometimes its show the montly and some time its show the annualy(and also thier sequnce is wrong) | Medium | Medium | its show the actual plan all time and also have a fixed a sequence of plan | iOS |  | Resolved | QA Production Approved
35 | BUG 35 |  | after "generate AI script" in hindi and if we click on regenerate then its translate content in english | High | High | its should regenerate in that particular language which selected by user | iOS |  | Resolved | QA Production Approved
36 | BUG 36 |  | without voice scroll script is auto moving but if we manually scoll up the script then its stop auto moving | High | High | after manually scroll script should run in auto mode | iOS |  | Resolved | QA Production Approved
37 | BUG 37 |  | after complete the video we edit the video and save as a draf video it take too much to save as draft(only first time it take too much time) | High | Medium | it should not take too much time to load | iOS |  | Resolved | QA Production Approved
38 | BUG 38 |  | sometimes after video we select the draft option then video apper in video section and as well as in draft section | Low | Low |  | iOS |  | Not feasible | Not Feasible
39 | BUG 39 |  | in draft section if we have multiple video then we not able to delete the multiple selected video (Suggestion) | High | High | it should have a multiple delete option | iOS |  | Resolved | QA Production Approved
40 | BUG 40 |  | support option not working | Critical | Critical | support option must be working | iOS |  | Resolved | QA Production Approved
41 | BUG 41 |  | after delete the draft video we go in video section and click on edit option then its show the error | High | High | after delete the draft video its should not show the error in main video preview | iOS |  | Resolved | QA Production Approved
42 | BUG 42 |  | in my plan continue button(it take too much time to load other data) | High | High |  | iOS |  | Resolved | QA Production Approved |  | sometime its not working in ios
43 | BUG 43 |  | after complete the video we delete the video but we come again in script then its show the preview of deleted video | High | High |  | iOS & Android |  | Resolved | QA Production Approved
44 | BUG 44 |  | if we have more then 3 script and we open the app then its render that some script is locked | High | High |  | Android |  | Resolved | QA Production Approved
45 | BUG 45 |  | we are subscribed user and we create more then 12 or script then in above message its show "script limit reached 3/3" | High | High |  | Android |  | Resolved | QA Production Approved
46 | BUG 46 |  | after subscription expired some time we are able to view more then 3 script | High | High |  | iOS |  | Resolved | QA Production Approved
47 | BUG 47 |  | we are able to move script out of screeen | High | High |  | iOS & Android |  | Resolved | QA Production Approved
48 | BUG 48 |  | after create the script > script is end but we are able to scroll the script are | Low | Medium |  | iOS |  | Resolved | QA Production Approved
49 | BUG 49 |  | in login > in email after enter the mail id we try to edit then cursor is end and type in end | Medium | Medium |  | iOS & Android |  | Resolved | QA Production Approved
50 | BUG 50 |  | after delete the script we go back then its redirect to the deleted script page | Medium | Medium |  | Android |  | Resolved | QA Production Approved
51 | BUG 51 | 21-07-2025 | add label in scroll speed(for increase and decrease) | Medium | Medium |  | iOS & Android |  | Resolved | QA Production Approved
52 | BUG 52 | 21-07-2025 | after start the video immediate we stop the video but in preview script is scrolling | Medium | Medium |  | iOS |  | Resolved | QA Production Approved
53 | BUG 53 | 21-07-2025 | if we start 7 or 10 second countdown then in countdown its not show 6(it go 7 to 5 second) | Low | Low |  | Android |  | Resolved | QA Production Approved
54 | BUG 54 | 25-07-2025 | after generate ai script its not show the script add button | High | High |  | iOS |  | Resolved | QA Production Approved
55 | BUG 55 | 23-07-2025 | if we are in last portion of script then"first line" is go up and came down inscript | Low | Low |  | iOS |  | Resolved | QA Production Approved
56 | BUG 56 | 23-07-2025 | if record the video and import video from phone then video is not merge | High | High |  | iOS |  | Resolved | QA Production Approved
57 | BUG 57 | 23-07-2025 | after add the clip we are on 2nd clip and we delete the clip but it still show thumbnail of deleted video | Low | Low |  | iOS |  | Resolved | QA Production Approved
58 | BUG 58 | 23-07-2025 | after merge the video its show the wrong timeline | Medium | Medium | https://www.awesomescreenshot.com/image/55599459?key=3a19ddf88c2f72ad107e88321caa83dc | iOS |  | Resolved | QA Production Approved
59 | BUG 59 | 23-07-2025 | it create a two copies of each video after save the video | High | High |  | iOS |  | Resolved | QA Production Approved
60 | BUG 60 | 23-07-2025 | without script we start the video immediate we stop the video and immediate start then time is start and video countdown is start and due to this i am not able to stop the recording(in any script for only first time when we record the video) | High | High |  | iOS & Android |  | Resolved | QA Production Approved
61 | BUG 61 | 23-07-2025 | we stop the video then button is loading but script and time is on | High | High |  | iOS & Android |  | Resolved | QA Production Approved
62 | BUG 62 | 23-07-2025 | if we stop speaking but script is scrolling | Critical | Critical |  | iOS |  | Resolved | QA Production Approved
63 | BUG 63 | 25-07-2025 | in script page its not the script limit message its show the black border | High | High |  | iOS |  | Resolved | QA Production Approved
64 | BUG 64 | 25-07-2025 | scroll speed option not work properly(state not manage) | Medium | Medium |  | iOS |  | Resolved | QA Production Approved
65 | BUG 65 | 25-07-2025 | in video section its show the message like script limit reached(5/10) but i have only 3 script | Medium | Medium |  | iOS |  | Resolved | QA Production Approved
66 | BUG 66 | 25-072025 | after go in script > in video start interface > script list button sensitivity is low | Medium | Medium |  | iOS & Android | Farhan | Resolved | QA Production Approved
67 | BUG 67 | 25-072025 | script list > we click on create new script then "ai script option and also save button is not working"(without any script hide edit button) | High | High |  | iOS |  | Resolved | QA Production Approved
68 | BUG 68 | 25-072025 | after compete the free script but in script list we selct the ai script then its not show the limit message | Low | Low |  | iOS & Android |  | Resolved | QA Production Approved
69 | BUG 69 | 25-07-2025 | if we stop the video in zero second then button is loading and not prepare the video | Medium | Medium |  | Android |  | Resolved | QA Production Approved
70 | BUG 70 | 29-07-2025 | tutorial not working properly | High | High |  | iOS |  | Resolved | QA Production Approved
71 | BUG 71 | 29-07-2025 | we select generate Ai Script and pop-up open but we cross the pop-up but it redirect to the add new script button | High | High |  | iOS |  | Resolved | QA Production Approved
72 | BUG 72 | 30-07-2025 | it allow more then 3 ai script(and also it allow if we delete the ai script then its allow to add one more ai script) | High | High |  | iOS & Android |  | Resolved | QA Production Approved
73 | BUG 73 | 2025-01-08 | in first script we select demo script then add script button disappear and also same scenario generate when we create first script and video from video tab | High | High |  | Android |  | Resolved | QA Production Approved
74 | BUG 74 | 2025-08-08 | without any script we go in video section then > select your script > create new script > ai script > ask ai to generate topic it not create the script after selecting the topic(but it count the script limit) | High | High |  | Android |  | Resolved | QA Production Approved
75 | BUG 75 | 2025-01-08 | in auto scroll we click on script then script pause and for start the script we have to do little scroll on script from bottom to up | Medium | Medium |  | Android |  | Not feasible | Not Feasible
76 | BUG 76 | 2025-01-08 | after delete video from video section then its show add button but if we comeback after changing the section then its not show add button in video section(after delete the last video) | Low | Low |  | iOS |  | Resolved | QA Production Approved
77 | BUG 77 | 2025-01-08 | in video section > after start the video we select the script but its not work with auto-scroll and voice scroll | High | High |  | iOS |  | Resolved | QA Production Approved
78 | BUG 78 | 2025-01-08 | sometimes on import video its show the "video merge failed" | High | High |  | iOS |  | Resolved | QA Production Approved
79 | BUG 79 | 2025-05-08 | after start the video its show the timer after three second(due to this it impact on script area and speed) | High | High |  | iOS |  | Resolved | QA Production Approved
80 | BUG 80 | 2025-05-08 | if we have common video in two videos and thier thumbnail is same and we delete the any same video then it delete the same video in two clips(and in first video its show the second clip) | High | High |  | iOS |  | Resolved | QA Production Approved
81 | BUG 81 | 2025-05-08 | if we record first with back camera and we record second clip with front camera then in second video frame is different | High | High |  | iOS |  | Resolved | QA Production Approved
82 | BUG 82 | 2025-05-08 | in video section > if we record without script then its loading the page and not convert in video | High | High |  | iOS |  | Resolved | QA Production Approved
83 | BUG 83 | 2025-05-08 | after record the clip we are not able hear audio and audio is not coming | High | High |  | iOS |  | Resolved | QA Production Approved
84 | BUG 84 | 2025-06-08 | if have two clip and we play the clip and press continue button then its redirect to the next page but in background we can hear the voice of last clip which we played | Medium | Medium |  | iOS |  | Resolved | QA Production Approved
85 | BUG 85 | 2025-06-08 | in script message its show the blank border | Low | Low |  | iOS |  | Resolved | QA Production Approved
86 | BUG 86 | 2025-06-08 | in ask ai to generate topic if we back then its redirect on main script screen instead of list screen | Medium | Medium |  | iOS |  | Resolved | QA Production Approved
87 | BUG 87 | 2025-06-08 | if make video through video tab but after completion of video its redirect on script page instead of video page(Suggestion) | Low | Low |  | iOS |  | Resolved | QA Production Approved
88 | BUG 88 | 2025-06-08 | add button in tutorial but after completion of tutorail add button is disappear(Suggestion) | Low | Low |  | iOS & Android |  | Resolved | Suggestion
89 | BUG 89 | 2025-06-08 | if have multiple clip then from second clip video is rotate to reverse | High | High |  | Android |  | Resolved | QA Production Approved |  | it take too much time to merge the video
90 | BUG 90 | 2025-06-08 | if we import the video then we try to merge the video then its page is loading(its skip the import video) | Critical | Critical |  | Android |  | Resolved | QA Production Approved |  | it skip some of the video due to corrupt video
91 | BUG 91 | 2025-06-08 | subscription issue(after completion of subscription period its not reflect in account) | Critical | Critical |  | iOS |  | Resolved | QA Production Approved |  | take time to update on server
92 | BUG 92 | 2025-06-08 | after purchase the subscription ai limit message take time too reflect the valid message(some time it show 3/3 script ans some time its show according to plan) | Low | Low |  | iOS & Android |  | Resolved | QA Production Approved
93 | BUG 93 | 2025-08-08 | after redeem the subscription we purhcase other script but it not reflect the account | Critical | Critical |  | iOS & Android |  | Resolved | QA Production Approved
94 | BUG 94 | 2025-08-08 | if we click multiple time on save button then whole sceen turn into black screen | High | High |  | iOS & Android |  | Resolved | QA Production Approved
95 | BUG 95 | 2025-11-08 | after a video one clip we delete but not save then we came back then its show the deleted clip(after delete we change page then show the pop-up) | High | High |  | iOS & Android |  | Resolved | QA Production Approved
96 | BUG 96 | 2025-12-08 | in video section not have scroller if we have multiple video | High | High |  | Android |  | Resolved | QA Production Approved
97 | BUG 97 | 13-08-2025 | at a time of start video it take pause on screen(for micro seconds) | Low | High |  | iOS |  | Not feasible | QA Production Approved
98 | BUG 98 | 13-08-2025 | if we try to add script plan after purchase it not reflect | Critical | High |  | iOS |  | Resolved | QA Production Approved
99 | BUG 99 | 13-08-2025 | it show the wrong sequence at a time of add script purchase | High | High |  | iOS |  | Resolved | QA Production Approved
100 | BUG 100 | 18-08-2025 | in video section we we click on cancel button then video is delete "button name mismatch" | High | High | button name should be correct | Android |  | Resolved | QA Production Approved
101 | BUG 101 | 18-08-2025 | at a time trim the video sometimes app is crash | Critical | Critical | app should not crash and functionality should be working | iOS |  | Resolved | QA Production Approved
102 | BUG 102 | 18-08-2025 | after log-out we go in any script and record the video and after the export the video its show the tutorial | Low | Low | after the video export its should not show the tutorial | Android |  | Resolved | QA Production Approved |  | after log-out this scenario is happen again due to fast operation in processing
103 | BUG 103 | 18-08-2025 | after start the countdown we go back then video stop but when we come and start again the countdown then its not show countdown in sequence | Low | Low | its should show the correct sequence | Android |  | Resolved | QA Production Approved
104 | BUG 104 | 25-08-2025 | trim button not working | High | High | trim button should be working | iOS |  | Resolved | QA Production Approved
105 | BUG 105 | 25-08-2025 | After purchase subscription > we create one or two script then its show the ai script limit message | High | High | it should not show ai limit message when we purchase the plan | iOS |  | Resolved | QA Production Approved
106 | BUG 106 | 26-08-2025 | after restore backup its delete the our current recorded videos from video section | High | High | restore backup should affect the video section | Android |  | Resolved | QA Production Approved
107 | BUG 107 | 26-08-2025 | at a time of create script i have only one script but we restore the backup then it show the old script also | High | High | it should only show the only script which we take create backup | Android |  | Resolved | QA Production Approved
108 | BUG 108 | 2025-01-09 | it take upto 1 hour time to update my plan | High | High | it should not take too much time to update | iOS |  | Resolved | QA Production Approved
109 | BUG 109 | 17-09-2025 | without and script > we go in video section > and click on create a script then whole screen is white(due to not handle execption) | High | High | it should be working | iOS |  | Resolved | QA Production Approved
110 | BUG 110 | 17-09-2025 | if we have coupon plan>and we close the app and come back then its not show the add script message | High | High | it should have add script optino | iOS |  | Resolved | QA Production Approved
111 | BUG 111 | 17-09-2025 | in free plan we utilize all ai script > and we take plan > after completion of plan we have less then 3 script then it allow once again 3 ai script | High | High | its should not allow to user | iOS |  | Not feasible | Not Feasible
112 | BUG 112 | 19-09-2025 | if we have promo code > plan then user is unable to create script offline because its not fetch the plan offline | High | High |  | iOS & Android |  | Not feasible | Not Feasible
113 | BUG 113 | 14-10-2025 | https://docs.google.com/document/d/1_FdTx2G72G95Mv86-ByU9zzoJLo-GXAEF0sQWfn76EE/edit?usp=sharing | Medium | High | it should be as per attached document | iOS & Android |  | Pending | Pending
114 | BUG 114 | 15-10-2025 | after create script in gujarti > in caption it detect only english words | High | High | it should as per user requirement | iOS |  | Not feasible | Not Feasible | Due to Assmebly AI API Limitation. | after video record in gujarati or indain regional language and in caption we select gujarati or other regional language like marathi then its show subtitle in hindi only
115 | BUG 115 | 15-10-2025 | after merge the video > go in style section > we go in mode > after selecting the "line by line" and "block" mode its show single word in caption(above menu of templetes) | High | High | it should be work as per caption mode | iOS |  | Resolved | Re-Open
116 | BUG 116 | 15-10-2025 | if we are create a new templete for caption > and in that caption we apply then it automatic select the default templete | High | High | its should be selected as per user | iOS |  | Resolved | Ready to Deploy
117 | BUG 117 | 15-10-2025 | in caption it take time load preview in caption screen | Medium | Medium | it should show the ral time preview | iOS |  | Resolved | Ready to Deploy |  | it start recording voice when time is start
118 | BUG 118 | 15-10-2025 | it not capture the sound of starting of the 2 or 3 second | High | High | it should capture the voice from the begining of video | iOS |  | Resolved | Pending
119 | BUG 119 | 15-10-2025 | at a time of caption screen video play button is not working | High | High | it should be working | iOS |  | Pending | Pending
120 | BUG 120 | 29-10-2025 | if selct the caption in hindi > and we select the differnet font(style) then its not apply | High | High | its should show according to the font style | iOS |  | Not feasible | Pending
121 | BUG 121 | 29-10-2025 | at a time style > in preview screen its not show the "shadow background" colour | Medium | High | its should show in preview screen | iOS |  | Resolved | Ready to Deploy
122 | BUG 122 | 29-10-2025 | in font > we apply italic > then some of the caption go out of caption background | Medium | High | its should not go out of caption background | iOS |  | Resolved | Ready to Deploy
123 | BUG 123 | 29-10-2025 | in font > after selcting any font style but when we choose "italic" and made the video but in final export its show the different font style(after selecting any style) | High | High | it should show the selected font style | iOS |  | Pending | Pending
124 | BUG 124 | 29-10-2025 | in caption > we choose spanish caption then in templets its show the spanish one but in video its show in english | High | High | it should show the selected caption language | iOS |  | Not feasible | Pending | its not translating that language its transcribe.
125 | BUG 125 | 29-10-2025 | in caption >we choose japanese caption then in templets its show the japaneses but in video its not show the caption | High | High | it should show the selected caption language | iOS |  | Not feasible | Pending | its not translating that language its transcribe.
126 | BUG 126 | 29-10-2025 | after video > in caption we select gujarati or other regional language like marathi then in templete and video its show the hindi caption | High | High | it should show the selected caption language | iOS |  | Not feasible | Pending
127 | BUG 127 | 31-10-2025 | after caption on > we play the video and and pause and then start video again from stating point then its continue from where we pause the video(it take too much time to update) | High | High | its should start as per user selected | iOS |  | Pending | Pending
128 | BUG 128
129 | BUG 129
130 | BUG 130
131 | BUG 131
132 | BUG 132
133 | BUG 133
134 | BUG 134

## Web - Bugs
Sr No | Bug_Id | Bug Identified Date | Module | Description | Severity | Priority | Proof | Current Result | Expected Result | Status | QA Name | Assign To | Environment | Deploy Date
1 | BUG_01 | 2025-06-24 | Script Editor | at a time of script generate if we select the 30 second but in your script section its show the 2 minutes(in actual its give the 30 second script) | High | High | https://vimeo.com/1093047890/a238a0215d?share=copy | at a time of generate script we select the 30 seconds but in your script its show the 2 minutes | in both interface time should be same | Pending | Manav | Hitesh Prajapati | Windows chrome
2 | BUG_02 |  | Record & teleprompter | if we start the record first time then we are not able to view the script from starting | High | High | https://vimeo.com/1093052722/e56bf1541d?share=copy | its not show the script from the start | its should show the script from start | Pending | Manav | Hitesh Prajapati | Windows chrome
3 | BUG_03 |  | Record & teleprompter | if we start the record first time then we are not able to scroll up and down the script | High | High | https://vimeo.com/1093052722/e56bf1541d?share=copy | we are not able to scroll up and down the script | its should allow to scroll up and down the script | Pending | Manav | Hitesh Prajapati | Windows chrome
4 | BUG_04 |  | Export & Share | if record the video and start then video first time then video progress bar is not run properly | High | High | https://vimeo.com/1093065487/f61da43ba4?share=copy | first time we play the video then progress bar is not working | its should all work properly | Pending | Manav | Hitesh Prajapati | Windows chrome
5 | BUG_05 |  | Record & teleprompter | if we record full video as per script and then complete the record but its not show export & share(may be long length is a issue) | Low | High | https://vimeo.com/1093067682/7dac3883da?share=copy | its not show the video if we record full script | its should show the recorded video | Pending | Manav | Hitesh Prajapati | Windows chrome
6 | BUG_06 |  | Record & teleprompter | on record page after completion one script and we select the other script or same script its loaded but open | High | High | https://vimeo.com/1093073000/f87be6ff01?share=copy | after completion of script we select other script then its loaded but not open | script should be open | Pending | Manav | Hitesh Prajapati | Windows chrome
7 | BUG_07 |  | Record & teleprompter | task notification take too much time to disappear | High | High | https://vimeo.com/1093599251/07ccf32e5b?share=copy | its take a too much to disappear notification | its should not take too much to diappear notification | Pending | Manav | Hitesh Prajapati | Windows chrome
8 | BUG_08 |  | Script Editor | if we create a script with the null data then (its open the last selected script) and allow to record the video | High | High | https://vimeo.com/1093612882/9a1e0167d7?share=copy | it allow to record with null data | its should not allow with the null script | Pending | Manav | Hitesh Prajapati | Windows chrome
9 | BUG_09 |  | Dashboard | (GUI BUG) new script card's alignment is not same as others | High | High | https://www.awesomescreenshot.com/image/54991607?key=fec87aefcebf1d3eaa5059d2b6d423fd | new script card's alignment is not same as others | all card alignment should be same | Pending | Manav | Hitesh Prajapati | Windows chrome
10 | BUG_10 |  | Export & Share | at a time of delete video its not show the confirmation message pop-up | High | High | https://vimeo.com/1093616385/fe91d205bc?share=copy | its not show the confirmation message pop-up at a time of delete the video | its should show the confirmation message pop-up at a time of delete the video | Pending | Manav | Hitesh Prajapati | Windows chrome
11 | BUG_11
12 | BUG_12
13 | BUG_13
14 | BUG_14
15 | BUG_15
16 | BUG_16
17 | BUG_17
18 | BUG_18
19 | BUG_19
20 | BUG_20
21 | BUG_21
22 | BUG_22
23 | BUG_23
24 | BUG_24
25 | BUG_25
26 | BUG_26
27 | BUG_27
28 | BUG_28
29 | BUG_29
30 | BUG_30
31 | BUG_31
32 | BUG_32
33 | BUG_33
34 | BUG_34
35 | BUG_35
36 | BUG_36
37 | BUG_37
38 | BUG_38
39 | BUG_39
40 | BUG_40
41 | BUG_41
42 | BUG_42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279

## Pivot Table 1
App Bugs Data |  |  |  | Web Bugs Data
COUNTA of Developer Status | Assign To |  |  | COUNTA of Priority | Assign To
Developer Status |  | Farhan | Grand Total | Priority |  | Hitesh Prajapati | Grand Total
| 0 |  | 0 |  | 0 |  | 0
Not feasible | 22 |  | 22 | High |  | 10 | 10
Pending | 4 |  | 4 | Grand Total | 0 | 10 | 10
Resolved | 98 | 1 | 99
Grand Total | 124 | 1 | 125
|  |  |  | Status | COUNTA of Status
0
|  |  |  | Pending | 10
QA Status | COUNTA of QA Status |  |  | Grand Total | 10
0
Not Feasible | 17
Pending | 9
QA Production Approved | 95
Re-Open | 1
Ready to Deploy | 4
Suggestion | 1
Grand Total | 127

## Reference App
Sr No | Reference App | Link
1 | Teleprompter with Video Audio by Pode Groups | Teleprompter with Video Audio - Apps on Google Play
2 | Teleprompter for Video by Norton Five Ltd | Teleprompter for Video - Apps on Google Play
3 | BIGVU Teleprompter for Videos | BIGVU Teleprompter & Captions - Apps on Google Play
4 | Teleprompter for Video | Teleprompter for Video - Apps on Google Play
5
6
7
8
9

## Features
Sr No | Feature | Link | Reference App | Pricing of Reference App
1 | Tutorial | In-App Tutorials: A Complete Guide in 2025
2 | In-app Notification
3 | Record Only Audio Option | Teleprompter with Video Audio - Apps on Google Play | Teleprompter with Video Audio by Pode Groups | 400 Rs for (Lifetime)
4 | Add logo On Video
5 | Change Background Of Video
6 | Option To Change Countdown
7 | Record Auto Stop (After Completion Of Script)
8 | Script Pause Option
9 | Font Style Change Option
10 | Voice Scroll Language(French,Russian) | Teleprompter for Video - Apps on Google Play | Teleprompter for Video by Norton Five Ltd | 2100 Rs 12 Month
11 | Mirror Option(Horizontal,Vertical)
12 | Automatically Add Subtitles After Recording
13 | Record In Portrait Or Landscape
14 | Focus On face
15 | Sign In Option With Google
16 | Auto Translate Your caption | BIGVU Teleprompter & Captions - Apps on Google Play | BIGVU Teleprompter for Videos | 2900 Rs 12 Month
17 | Import Script From PDF,DOCX,TXT | Teleprompter for Video - Apps on Google Play | Teleprompter for Video | 2000 Rs LifeTime